## Slide 1: project name : electronic pharmacy project sponsor :Ministry of Health project manager :hala khalid Mohamed

## Slide 2: Purpose of the project:
Saving time and facilitating the process of buying medicines while maintaining health and distance in the presence of the Corona virus

## Slide 3: Business Case
It is an electronic pharmacy that consists of a group of automated vending machines, where the medicines required by the user are stored and contain a scanner to take input from the user, and the prescription must contain a barcode that the user recognizes.
the systemPlenty of space for medicine storage. Contains inventory control to keep track of inventory. Specifies the time required to store the drug, the expiration date and the expiry date of the drug. Sends alerts to refill the pantry when medication runs out. It has a working system for receiving money from the user for dispensed drugs. It also contains a micro-central processing of systems monitoring and a programmer to receive input from the user via a scanner.

## Slide 4
The project time: 22 week.. The budget :is about 100,000.

## Slide 5: Risk and Issue Management Plan
1-Lack of required resources (eg medicines and other products) resulting in project delays. 2-The specified budget is not sufficient for the project. 3-The absence of one of the programmers who specialize in completing
programs from the team. 4-Failure to complete the project on time

## Slide 6: Communication Management Plan:
Meeting every week at seven in the evening

## Slide 7
Deliverables
[1] hardware requirement.
[2]design.
[3]machine operating system(OS)

## Slide 8
Project milestones
[1] hardware requirement time : 6week:budget[10.000]
A scanner is manufactured that reads the prescription, and has a servo drug
dispensing.
It has a large space for storing medicines.
It also includes an inventory control system to keep track of inventory
Contains a central microprocessor Monitors all systems, programmer and
receiver for input from the user through the scanner, and operates and controls all components needed to dispense medication requested by the user.

## Slide 9
[2]design : time : 8week:budget[50.000]
The design of the machines will be manufactured
from where:
-Design of the machine
-Design of the user interface
-Design of storage space
-Design of pill singulation system

## Slide 10
[3]machine operating system(OS):time 8week:budget[40.000]
We will begin to manufacture the system, where the hardware will be combined with the design and write the code to run the system, use the algorithm, and use programmers and developers.

## Slide 11: Project scope statement
*The objectives of the project are:
*The medicines used do not have adverse side effects on the client .
*The cosmetics used do not need medical supervision, meaning that they are safe.
*The used vending machines are available in more than one place (such as the mall) later on, so the customer does not have to go to a particular pharmacy to ask about cosmetics, for example.
*And in the light of Corona, it will be safe because the process of buying and selling is between the customer and the machine only.

## Slide 12: *Assumptions
The system is expected to succeed and will be applied to private hospitals as well as pharmacies because it is characterized by speed, reliability and safety. It also facilitates the purchase process for the buyer and saves time as well.

## Slide 13: Project exclusions*
This project will be applied to private hospitals only, which will be equipped with a barcode feature to help the system read the prescription.

## Slide 14: Constraints*
*This project must be delivered within the specified budget .
*this project must be delivered At the appointed time
*The medicines used are naturally documented and do not have serious harm

## Slide 15
1.medicine vending machine
1.1hardware requirement
1.2scanner
1.2.1design
1.2.2.Design of the machine
1.3Large space
1.4sensors
1.5Inventory motoring system
1.2.3Design of the user interface
1.2.4Design of storage space
1.2.5Design of pill singulation system
1.3.1machine operating system(OS)
I1.3.2ntegration hardware with design
1.3.3coding
1.3.4algorithm
1.6Central microprocess
1.4.1FULL TEST
WBS

## Slide 16: WBS DICTIONARY
CODE OF ACCOUNTS NUMBER
1.1hardware requirement
1.2scanner
1.3Large space
1.4sensors
1.5Inventory motoring system
1.6Central microprocess

## Slide 17
1.2.1design
1.2.2.Design of the machine
1.2.3Design of the user interface
1.2.4Design of storage space
1.2.5Design of pill singulation system
1.3.1machine operating system(OS)
I1.3.2ntegration hardware with design
1.3.3coding
1.3.4algorithm
1.4.1FULL TEST

## Slide 18: DESCRIPTION OF THE WBS ELEMENTS
[1] hardware requirement
A scanner is manufactured that reads the prescription, and has a servo drug
dispensing.
It has a large space for storing medicines.
It also includes an inventory control system to keep track of inventory
Contains a central microprocessor Monitors all systems, programmer and
receiver for input from the user through the scanner, and operates and controls all components needed to dispense medication requested by the user.

## Slide 19
2]design :
The design of the machines will be manufactured
from where:
-Design of the machine
-Design of the user interface
-Design of storage space
-Design of pill singulation system

## Slide 20
[3]machine operating system(OS)
We will begin to manufacture the system, where the hardware will be combined with the design and write the code to run the system, use the algorithm, and use programmers and developers.

## Slide 21
**RESPONSIBLE OF THE WBS
MINISTRY OF HEALTH
And eng /Mohamed mokhtar
COST TO CREAT THE WBS
100.000

## Slide 22: Responsibility Matrix
DEMINA | MANAR NASR | HALA REFAT | HALA KHALID | TASK
S | S | S | R | hardware requirement
I | C | R | S | scanner
S | S | R | I | Large space
I | R | C | S | sensors
R | S | S | S | Inventory motoring system
C | S | S | R | Central microprocess
 | S | R | C | design
R | S | C | S | Design of the machine
S | C | R | S | Design of the user interface
C | R | S | S | Design of storage space
I | C | S | R | Design of pill singulation system
C | I | R | S | machine operating system(OS)
R | I | C | S | integration hardware with design
S | S | I | R | coding
C | R | S | S | Algorithm
S | I | S | R | Full test

## Slide 23
NETWORK:
activity time(week) | preceding activity | description | ACTIVATY
2 | Non | design of the machine | A
6 | D | Coding | B
4 | A | Design of storage space | C
2 | G | Design of user interface | D
2 | C,G | Scanner | E
4 | C,G | Sensor | F
2 | E,F | Integration of hardware with design | G

## Slide 24
8 | B3 | 2
2 | Coding | 2
10 | 6 | 4
12 | G7 | 10
0 | integration hardware with design | 0
12 | 2 | 10
6 | C2 | 2
0 | Design of storage space | 0
6 | 4 | 2
4 | D4 | 2
6 | Design of the user interface | 6
10 | 2 | 8
2 | A1 | 0
0 | design of the machine | 0
 | 2 | 0
10 | F6 | 6
0 | Scanner | 0
10 | 4 | 6
 | E5 | 6
2 | sensor | 2
10 | 2 | 8
EF | ID | ES
SL | RES | SL
LF | DUR | LS
Critical path is :A,C,F,G

## Slide 25
Resource Constrained Project
14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | SL | LF | ES | DUR | RES | ID
 |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 | 0 | 2 | 0 | 2 | 2P | 1
 |  |  |  |  | -- | -- | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 12 | 6 | 6 | 2P | 2
 |  |  |  |  |  |  |  |  | 2 | 2 | 2 | 2 |  |  | 0 | 6 | 2 | 4 | 2P | 3
 |  |  |  |  | -- | -- | -- | -- | -- | -- | 1 | 1 |  |  | 2 | 6 | 2 | 2 | 2P | 4
 |  |  |  |  | -- | -- | 1 | 1 |  |  |  |  |  |  | 2 | 12 | 10 | 2 | 1P | 5
 |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  |  |  | 0 | 10 | 6 | 4 | 1P | 6
 |  |  | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 2 | 14 | 12 | 2 | 1P | 7
 | 1P | 1P | 3P | 3P | 3P | 3P | 3P | 3P | 2P | 2P | 3P | 3P | 2P | 2P |  |  |  |  |  | TR
 | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P | 3P |  |  |  |  |  | RA

## Slide 26
Time Phased Budget
14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | BUDGET | TASK | DUR | ID
 |  |  |  |  |  |  |  |  |  |  |  |  |  | 20 | 20.000 | design of the machine | 2 | 1
 |  |  |  |  |  |  |  |  |  |  | 10 | 10 | 10 |  | 30.000 | Coding | 6 | 2
 |  |  |  |  |  |  |  |  |  | 10 | 5 | 5 |  |  | 20.000 | Design of storage space | 4 | 3
 |  |  |  |  |  |  |  | 1 |  |  |  | 9 |  |  | 10.000 | Design of user interface | 2 | 4
 |  |  |  |  |  |  | 5 | 4 | 3 | 2 | 1 |  |  |  | 5.000 | Scanner | 2 | 5
 |  |  |  |  |  |  |  | 1 | 2 | 2 |  |  |  |  | 5.000 | Sensor | 4 | 6
 |  |  | 4 |  | 2 | 3 |  | 1 |  |  |  |  |  |  | 10.000 | Integration of hardware with design | 2 | 7
 |  |  | 1 | 1 | 2 | 3 | 5 | 7 | 5 | 14 | 16 | 24 | 10 | 20 | 100.000 |  |  | WT
 |  |  | 100 | 99 | 98 | 95 | 90 | 83 | 78 | 64 | 48 | 24 | 14 | 0 |  |  |  | C

## Slide 27
Team members
[1]hala khalid mohamid
[2] manar nasr
[3]nashwaa refat
[4]damiana luka.